## Sheet1
Risk | Likelihood | Effect | Mitigation Plan
1. Delays in project timeline | Medium | Key functionalities may not be ready in time for testing or launch. | Create a detailed project schedule with milestones and regular progress reviews.
2. Incomplete or ambiguous requirements | High | Development and testing may not align, leading to missed functionality or defects. | Conduct requirement walkthroughs with all stakeholders to clarify ambiguities.
3. Payment gateway failures | Medium | Failed payments may lead to loss of bookings and user dissatisfaction. | Use a reliable payment API, and add retry mechanisms for failed transactions.
4. Poor communication among stakeholders | Low | Misunderstandings may lead to rework and reduced team efficiency. | Schedule regular team meetings and use effective collaboration tools.
5. Poor performance under high traffic | Medium | Slow response times or crashes during peak usage, such as ticket sales. | Optimize the system for scalability and conduct load testing.